## Protokoll
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2025-03-20
Group Number |  | 16
Participant 1 |  | Andak Kadir Resul
Participant 2 |  | Liu Yueting
Participant 3 |  | Reithmaier Melanie
Participant 4 |  | Sabic Kenan
Participant 5 |  | Tekin Beyza
Mentor |  | Docsek Martin
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | CSS Grundlayout | 3 | 2 | -1 | 1
2 | HTML Struktur anhand Design | 2 | 1 | -1 | 1 |  | Mehr Links müssen erstellt werden, Buttons müssen noch getestet werden
3 | GitHub aufsetzen | 1 | 0.5 | -0.5 | 1
4 | ERM-Diagramm für Datenbank | 4 |  | -4
4 |  |  |  | -6.5 | 3 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Retrospektive + nächster Sprint
Retrospektive | Nächste Schritte im nächsten Sprint
Was lief gut? Strukturiertes und sauberes Grundlayout Effiziente Integration von Bootstrap Gute Teamkommunikation und klare Aufgabenteilung Was können wir besser machen? Frühere Definition der responsiven Breakpoints, um zusätzlichen Aufwand zu vermeiden, Ausführlichere Code-Dokumentation zur besseren Nachvollziehbarkeit, Regelmäßigere Tests, um Fehler frühzeitig zu erkennen | Weiterentwicklung des Designs und zusätzliche Detailoptimierungen im CSS. Implementierung weiterer interaktiver Komponenten (z. B. Formulare, Animationen). Verbesserung der Dokumentation und Einrichtung automatisierter Tests für responsives Design. Datenbank erstellen in mySQLi